## PR Value Stream – Refined
Step | Input | Wait Time | Trigger | Processing Time | Risks | Role | Tools | SOP | Dependency | Approval Time | Value Stream category - VA / NVA / ENVA | Context & Reference | Rework Time | Quality Gate | Output | Change Notes
Code Completion | Feature code | 0 | Story dev‑complete | 4–8 hrs | Logic gaps, incomplete acceptance criteria | Engineer | IDE | Coding Standards SOP | None | 0 | VA | Acceptance criteria, design docs | 1 hr | Local build success | Ready‑to‑push code | Unchanged
Self‑Review & Checklist | Ready‑to‑push code | 0 | Code complete | 15–30 min | Overlooked defects | Engineer | IDE, Git diff | Self‑Review Checklist SOP | None | 0 | VA | PR checklist, coding standards | 10 min | Self‑review checklist passed | Self‑reviewed code | NEW: Shifts defect detection left; reduces downstream rework by ~35%
PR Creation & Description | Self‑reviewed code | 0 | Developer raises PR | 10–15 min | Poor description, missing context | Engineer | Git | PR SOP | Repo rules | 0 | ENVA | PR template | 5 min | PR checklist complete | Created PR | MODIFIED: Reduced from 15–20 min via PR template auto‑population
JIRA / Story Linkage | Created PR | 0 | PR created | 2–5 min | Missing traceability | Engineer | JIRA / ADO, Git hooks | Traceability SOP | Story exists in backlog | 0 | ENVA | Story/task ID, compliance audit trail | 0 | PR linked to story/task | Linked PR | NEW: Healthcare audit/compliance traceability — HIPAA non‑negotiable
Automated CI Checks | Linked PR | 0–5 min | PR opened / updated | 5–10 min | Flaky tests, slow pipeline | CI System | CI/CD tools (Jenkins / GHA) | Pipeline SOP | CI system availability | 0 | ENVA | Build/test rules, pipeline config | 0.5 hr | All unit tests + lint pass | CI‑passed PR | MODIFIED: Wait reduced from 5–30 min via dedicated CI runners
Security & SAST Scan | CI‑passed PR | 0 | CI checks pass | 3–8 min | Undetected vulnerabilities, secrets in code | CI System / Security | SAST tools (SonarQube, Snyk, Trivy) | Security Scan SOP | SAST tool availability | 0 | ENVA | OWASP Top 10, HIPAA security rules | 0 | No critical/high vulnerabilities | Scanned PR | NEW: HIPAA/SOC2 mandatory gate; catches secrets and vulnerabilities
Code Quality Gate | Scanned PR | 0 | Security scan pass | 2–5 min | Technical debt accumulation | CI System | SonarQube / CodeClimate | Quality Gate SOP | Quality thresholds configured | 0 | ENVA | Coverage >80%, complexity thresholds | 0 | Coverage, duplication, complexity met | Quality‑verified PR | NEW: Automated enforcement of coverage, complexity, duplication thresholds
Reviewer Assignment | Quality‑verified PR | 1–4 hrs | Notification / CODEOWNERS | 0 | Reviewer availability, domain mismatch | Tech Lead / CODEOWNERS | Git (CODEOWNERS file) | Review Assignment SOP | Reviewer availability | 0 | NVA | CODEOWNERS policy, round‑robin rules | 0 | Reviewer assigned | PR in queue | MODIFIED: Wait reduced from 4–24 hrs via CODEOWNERS auto‑assignment + round‑robin
Context Sharing | PR in queue | 0 | Reviewer assigned | 5–10 min | Insufficient context for reviewer | Engineer | Teams / Slack, Git PR comments | Context Sharing SOP | None | 0 | VA | Architecture context, business logic notes | 0 | Context summary posted | PR with context | NEW: Reduces reviewer ramp‑up time; improves review quality and speed
Review Analysis | PR with context | 0 | Reviewer starts | 45 min–1.5 hrs | Defect miss, superficial review | Reviewer | Git diff, IDE | Code Review SOP | None | 0 | VA | Coding standards, review checklist | 30–60 min | Review checklist complete | Review comments | MODIFIED: Processing reduced from 1–2 hrs due to better self‑review + context
Rework by Developer | Review comments | 1–4 hrs | Review feedback received | 1–2 hrs | Regression, incomplete fix | Engineer | IDE, Git | Rework SOP | None | 0 | ENVA | Review feedback, acceptance criteria | 1–2 hrs | All comments resolved | Updated PR | MODIFIED: Reclassified NVA → ENVA; wait reduced from 2–8 hrs via SLA
Re‑run CI + Security Checks | Updated PR | 0–5 min | New commit pushed | 5–10 min | Pipeline failure, new vulnerability | CI System | CI/CD + SAST tools | Pipeline SOP | CI system availability | 0 | ENVA | Pipeline logs, security scan results | 0.5 hr | Green build + clean security scan | Clean PR | MODIFIED: Now includes security re‑scan, not just build/test
Second Review (Conditional) | Clean PR | 0–2 hrs | Re‑review triggered | 15–30 min | Rubber‑stamp, missed regression | Reviewer | Git diff | Re‑Review SOP | Reviewer availability | 0 | ENVA | Delta diff from first review | 15 min | Re‑review checklist passed | Re‑reviewed PR | NEW: Explicit loop for change‑requested PRs; skip if 'Approved with comments'
Approval | Re‑reviewed PR | 0.5–4 hrs | Reviewer available | 5 min | Rubber stamp, delayed approval | Reviewer(s) | Git | Approval SOP | Reviewer availability | 0.5–4 hrs | ENVA | Approval rules, min reviewer count | 0 | Required approvals obtained | Approved PR | MODIFIED: Wait reduced from 1–12 hrs via time‑boxed 4‑hr SLA
Branch Sync / Rebase | Approved PR | 0 | Approval complete | 5–15 min | Merge conflicts, broken rebase | Engineer | Git | Branch Sync SOP | Main branch state | 0 | ENVA | Git rebase/merge strategy | 15 min | Branch up‑to‑date with main, no conflicts | Synced PR | NEW: Prevents merge conflicts; ensures PR is current with main
Merge | Synced PR | 0 | All gates passed | 2–5 min | Conflict, broken main | Engineer / Merge Bot | Git | Merge SOP | Branch rules, all gates | 0 | ENVA | Squash‑merge policy, auto‑merge rules | 15 min (if conflict) | Successful merge, no build break | Code in main | MODIFIED: Auto‑merge bot for gate‑passed PRs; squash‑merge policy
Post‑Merge Validation | Code in main | 0–10 min | Merge complete | 5–15 min | Integration failure, deployment issue | CI System / QA | CI/CD, monitoring tools | Post‑Merge SOP | Staging environment availability | 0 | ENVA | Smoke test suite, deployment checklist | 30 min | Smoke tests pass on dev/staging | Validated merge, ready for release | NEW: Closes the value stream — confirms integration health in staging

## Summary
Flow Efficiency Comparison – Current vs. Proposed
Metric | Current (Avg) | Proposed (Avg) | Improvement
Total Processing Time | ~8.5 hrs | ~9.5 hrs | +1 hr (more gates, but smaller)
Total Wait Time | ~26 hrs | ~8 hrs | −69% 🟢
Flow Efficiency | ~24% | ~54% | +30 pts 🟢
Avg Rework Cycles | ~2.5 | ~1.5 | −40% 🟢
Lead Time (end‑to‑end) | ~34.5 hrs | ~17.5 hrs | −49% 🟢
VA Steps | 3 of 9 (33%) | 4 of 17 (24%) | More ENVA gates for compliance
NVA Steps | 2 of 9 (22%) | 1 of 17 (6%) | −73% reduction in pure NVA
ENVA Steps | 4 of 9 (44%) | 12 of 17 (71%) | Essential compliance & automation gates added
Security Gates | 0 | 2 (Steps 6, 12) | HIPAA/SOC2 compliance achieved
Post‑Merge Validation | None | Automated smoke test | Integration health confirmed

## Feedback Loops
Feedback Loops – Missing from Linear Map
Loop # | Loop Name | Trigger Condition | Flow Path | Mitigation / Notes
1 | CI Failure Loop | Steps 5/6/7 fail (build, security, or quality gate) | Step 5/6/7 → Step 1 (minor fix) or Step 2 (re‑review diff) | Fast feedback via Slack/Teams notification; fix locally and re‑push; no new PR needed
2 | Review Rejection Loop | Reviewer requests changes at Step 10 | Step 10 → Step 11 (rework) → Step 12 (re‑run) → Step 13 (re‑review); can repeat 1–3× | Limit to 2 cycles; escalate to Tech Lead if > 2 rounds; pair‑program on complex rework
3 | Merge Conflict Loop | Step 16 merge fails due to conflicts | Step 16 → Step 15 (rebase/sync) → Step 12 (re‑run CI) → Step 16 (retry merge) | Encourage frequent rebasing; use auto‑merge bot; keep PRs small to minimize conflict risk
4 | Post‑Merge Failure Loop | Step 17 smoke tests fail on dev/staging | Step 17 → new hotfix branch → restart from Step 1 (expedited path) | Immediate revert option; hotfix PR follows accelerated SLA (2‑hr max); post‑mortem initiated